## LP - OBRAS
WORKS PROVIAS NACIONAL YEAR 2024
# | NOMENCLATURE | NAME | AMOUNT | PARTICIPANTS REGISTRATION | INQUIRES AND OBSERVATIONS | BASE INTEGRATION | PRESENTATION | QUALIFICATION | CONFIRMATION | COMMITTEE | COMMENTS
2 | LP-SM-1-2024-MTC/20-1 | WORK: CONTRACTING OF THE EXECUTION OF THE WORK: CONSTRUCTION OF 11 ROAD BRIDGES ON THE NATIONAL ROAD NETWORK, ROUTE PE-1NR ON THE TAMBOGRANDE-MORROPON-CHULUCANAS STRETCH, PIURA | 585101683.03 | 12/01/2024 TO 29/09/2024 | 12/01/2024 UNTIL 07/02/2024 | 2024-09-19 | Submission of bids (Electronic) 30/09/2024 DE 00:01 HASTA 23:59 HRS.. | 01 - 02/10/2024 | 2024-10-03 | 1 HARLEM BRAVO CASTAÑEDA Main Chairman 2 RODOLFO SAMUEL CHIRI UBILLUS Main Member 1 3 KEVIN ANDERSON RAMIREZ SARAVIA Main Member 2 4 JHONNY ALEX ORIZANO PEREZ Substitute President 5 JUAN JESUS VENTURA ROQUE Substitute Member 1 6 JUAN CARLOS CASTILLO VASQUEZ Substitute Member 2 | SUMMONED... 12 SEPTEMBER 2024, POSTPONED THE STATEMENT OF ACQUITTAL OF QUERIES AND OBSERVATIONS AS THE RESPONSES REGARDING THE RIGHT OF WAY ARE STILL PENDING.
1 | LP-SM-6-2024-MTC/20.-1 | PROJECT: CONSTRUCTION AND COMPLETION OF THE REHABILITATION AND IMPROVEMENT OF THE LIMA- CANTA- LA VIUDA - UNISH ROAD, LIMA- CANTA SECTION | 91171665.8 | 15/08/2024 UNTIL 30/09/2024 | 15/08/2024 UNTIL 28/08/2024 | 2024-09-20 | Submission of bids (Electronic) 01/10/2024 FROM 00:01 UNTIL 23:59 HRS.. | 02 - 04/10/2024 | 2024-10-09 | 1 ALVARO ALONSO SOTELO GUILLEN Main Chairman 2 JOSE CARLOS PACHECO MACEDO Main Member 1 3 KEVIN ANDERSON RAMIREZ SARAVIA Main Member 2 4 MIGUEL ANGEL HUAPAYA AMES Substitute President 5 MANUEL NAHON VIDAL VELASQUEZ Substitute Member 1 6 EMERSON JUNIOR SANTON MEZA Substitute Member 2 | SUMMONED...16 SEPTEMBER 2024: POSTPONED SINCE THE USER AREA HAS NOT SUBMITTED A STATEMENT OF ACQUITTAL...
3 | LP-SM-3-2024-MTC/20-1 | WORK: Improvement of the Boca del Río - Tacna road in the districts of Tacna, Sama and La Yarada Los Palos in the Province of Tacna - Department of Tacna. | 726631186.69 | 18/06/2024 UNTIL 15/10/2024 | 18/06/2024 UNTIL 01/07/2024 | 2024-10-02 | Submission of bids (Electronic) 16/10/2024 FROM 00:01 UNTIL 23:59 HRS.. | 17 - 21/10/2024 | 2024-10-21 | 1 JOEL EDILBERTO BULLON CHURAMPI Main Chairman 2 ARINIA GLADYS SANTIAGO MELENDEZ Main Member 1 3 PERCY ALEX JURADO CARRASCO Main Member 2 4 JUAN ALFONSO ARENAS DAMIAN Substitute President 5 MIGUEL ANGEL HUAPAYA AMES Substitute Member 1 6 MARCOS ABEL NUÑEZ ALVAREZ Substitute Member 2 | 16 SEPTEMBER 2024: POSTPONED due to pronouncement of the user area regarding the queries and observations related to the requirement.
6 | LP-SM-8-2024-MTC/20-1 | CONTRACTING OF THE EXECUTION OF THE WORKS: CONSTRUCTION OF THE JUANA RIOS BRIDGE AND ACCESSES | 94639661.41 | 12/09/2024 UNTIL 15/10/2024 | 12/09/2024 UNTIL 25/09/2024 | 2024-10-02 | Submission of bids (Electronic) 16/10/2024 FROM 00:01 UNTIL 23:59 HRS.. | 17 - 21/10/2024 | 2024-10-21 | 1 JUAN ALFONSO ARENAS DAMIAN Main Chairman 2 JHONNY ALEX ORIZANO PEREZ Main Member 1 3 LUIS ADOLFO SUAREZ LEYVA Main Member 2 4 EMERSON JUNIOR SANTON MEZA Substitute President 5 HARLEM BRAVO CASTAÑEDA Substitute Member 1 6 SVEN HART BAUTISTA CONDORI Substitute Member 2 | SUMMONED...
| LP-SM-7-2024-MTC/20-1 | REHABILITATION AND IMPROVEMENT OF THE ROAD EMP. RUTA 18A (PTE. RANCHO) - CHAGLLA- RUMICHACA, STRETCH I | 579944500.81 | 18/09/2024 UNTIL 21/10/2024 | 18/09/2024 UNTIL 01/10/2024 | 2024-10-10 | Submission of bids (Electronic) 22/10/2024 FROM 00:01 UNTIL 23:59 HRS.. | 23 - 28/10/2024 | 2024-10-28 | 1 EMERSON JUNIOR SANTON MEZA Main Chairman 2 MARTHA CECILIA HERRERA MONTEALEGRE Main Member 1 3 VICTOR MANUEL CHAVEZ BENAVENTE Main Member 2 4 GUISELA MARTINEZ ORE Substitute President 5 MAURO CESAR CHARALLA PFUÑO Substitute Member 1 6 JUAN DAVID SILVA ARANIBAR Substitute Member 2 | SUMMONED...

## CONSERV SERVICIOS & ADJ SIMP _
PRESERVATIONS Provias Nacional - 2024
# | NOMENCLATURE | NAME | AMOUNT | PARTICIPANTS REGISTRATION | INQUIRES AND OBSERVATIONS | BASE INTEGRATION | PRESENTATION | QUALIFICATION | CONFIRMATION | COMMITTEE | COMMENTS
1 | AS-SM-18-2024-MTC/20-1 | ROAD MANAGEMENT AND MAINTENANCE SERVICE BY LEVEL OF SERVICE OF THE ROAD CORRIDOR: ANYANGA - HUARI - PTE POMACHACA/ ANYANGA - HUANTAR - PTE POMACHACA - ANRA - HUACAYBAMBA - JIRCAN - CARPA - PIRUSH - MONZON - CACHICOTO - TINGO MARÍA / DV. ANRA - DV PAUCAS/ EMP. PE-14 A (PIRUSH) - CONTADERA - CHAPACARA - EMP. PE-14 A | 177061833.16 | 07/09/2024 UNTIL 22/09/2024 | 07/09/2024 UNTIL 10/09/2024 | 2024-09-18 | Submission of bids (Electronic) 23/09/2024 FROM 00:01 UNTIL 23:59 HRS.. | 24 - 26/09/2024 | 2024-09-26 | 1 GUISELA MARTINEZ ORE Main Chairman 2 ELVIS SANDRO VEGA ARANGURE Main Member 1 3 JAVIER ANIBAL MONTOYA NU¿EZ Main Member 2 4 JUAN ALFONSO ARENAS DAMIAN Substitute President 5 SONIA PALACIOS PALACIOS Substitute Member 1 6 MILUSKHA PAMELA COJAL VIGO Substitute Member 2 | SUMMONED...12 SEPTEMBER 2024: To postpone the absolution stage of queries and observations and integration of the bases of the Simplified Adjudication Nº 0018-2023-MTC/20 resulting from the Public Tender N° 0026-2023-MTC/20 so that the user area submits its pronouncement on the queries and observations; and after that to be consolidated and reviewed by the selection committee, and therefore the subsequent stages.
2 | AS-SM-20-2024-MTC/20-1 | MANAGEMENT, IMPROVEMENT AND ROAD MAINTENANCE SERVICE BY LEVELS OF SERVICE OF THE ROAD CORRIDOR: EMP. PE - 3S (DV. IMPERIAL) - PAMPAS - ABRA INDEPENDENCIA - CHURCAMPA - EMP. PE - 3S (MAYOCC) / EMP. PE - 3S (LA MEJORADA) - PUCACRUZ - ACOBAMBA - CAJA - MARCAS - EMP. PE - 3S (ALLCOMACHAY PE.) | 370820196 | 11/09/2024 UNTIL 22/09/2024 | 11/09/2024 UNTIL 12/09/2024 | 2024-09-18 | Submission of bids (Electronic) 23/09/2024 FROM 00:01 UNTIL 23:59 HRS.. | 24 - 26/09/2024 | 2024-09-26 | 1 DAVID FERNANDO MAYORGA LIZARRAGA Main Chairman 2 JUAN CARLOS CASTILLO VASQUEZ Main Member 1 3 PERCY NEYER LOPEZ MEDINA Main Member 2 4 SONIA PALACIOS PALACIOS Substitute President 5 JOEL EDILBERTO BULLON CHURAMPI Substitute Member 1 6 JOHAN LUIS SANTA CRUZ PAREDES Substitute Member 2 | SUMMONED...16 SEPTEMBER 2024: The stages of the selection procedure are postponed due to the fact that the user area will send the tender documents on 18-9-24.
3 | AS-SM-19-2024-MTC/20-1 | MANAGEMENT, IMPROVEMENT AND ROAD MAINTENANCE SERVICE BY LEVELS OF THE ROAD CORRIDOR: EMP. PE-1S (BRIDGE LOS MAESTROS) - PARCONA - TAMBILLO - EMP. PE - 28A (HUAYTARÁ)/EMP. PE - 1S (CHINCHA ALTA) - PTE HUACHINGA - EMP. PE-28D (LACHOCC) / EMP. PE-1S (DV PARACAS) - PARACAS - PTO. SAN MARTIN / EMP. PE - 1SE (MALPASO) - SAN CLEMENTE - DV. PISCO - EMP. PE-1SE /EMP. PE 1S DV. SAN ANDRES - SAN ANDRES - PE 1SF / PE -1SG - EMP.PE 28 - PARACAS | 396443891.14 | 11/09/2024 UNTIL 22/09/2024 | 11/09/2024 UNTIL 16/09/2024 | 2024-09-18 | Submission of bids (Electronic) 23/09/2024 FROM 00:01 UNTIL 23:59 HRS.. | 24 - 27/09/2024 | 2024-09-27 | 1 EMERSON JUNIOR SANTON MEZA Main Chairman 5 MILUSKHA PAMELA COJAL VIGO Main Member 1 6 HENRY ESTEBAN CARRILLO VILLEGAS Main Member 2 2 JOEL EDILBERTO BULLON CHURAMPI Substitute President 3 SONIA PALACIOS PALACIOS Substitute Member 1 4 ELMER CALIXTO MELGAREJO NORABUENA Substitute Member 2 | SUMMONED…
4 | AS-SM-10-2024-MTC/20-1 | MANAGEMENT AND MAINTENANCE SERVICES BY SERVICE LEVELS OF THE ROAD CORRIDOR: BAPPO - BAYOVAR - SECHURA - CATACAOS - PIURA / LAMBAYEQUE - OLMOS/PRIMAVERA BRIDGE-AV. GUARDIA CIVIL-AV. LUIS MONTERO-AV. PROGRESO-DV. CATACAOS (EMP. PE-1N) | 50794227.92 | 03/08/2024 UNTIL 24/09/2024 | 03/08/2024 UNTIL 08/08/2024 | 2024-09-20 | Submission of bids (Electronic) 25/09/2024 FROM 00:01 UNTIL 23:59 HRS.. | 26 - 30/09/2024 | 2024-09-30 | 2 FLOR ALEXANDRA ALFARO CARBAJAL Main Chairman 3 SONIA PALACIOS PALACIOS Main Member 1 4 EDGAR SABINO ALARCON HUALLPA Main Member 2 5 EMERSON JUNIOR SANTON MEZA Substitute President 6 PERCY OMAR CAMONES RONDAN Substitute Member 1 1 JAVIER ANIBAL MONTOYA NUÑEZ Substitute Member 2 | SUMMONED... 13 SEPTEMBER 2024: Postponed due to observations on the specifications of the user area and considering the deadlines for review and management by the committee.
5 | AS-SM-17-2024-MTC/20-1 | ROAD MANAGEMENT AND MAINTENANCE SERVICE BY SERVICE LEVELS OF THE ROAD CORRIDOR: EMP. PE-18 (DV. RÍO SECO) - SAYÁN - CHURÍN - OYÓN Y EMP. PE-1NE (HUAURA)- DV. ANDAHUASI (PE-18) /ACOS - HUAYLLAY (PE-20 A) | 74906047.55 | 18/09/2024 UNTIL 26/09/2024 | 18/09/2024 UNTIL 19/09/2024 | 2024-09-23 | Submission of bids (Electronic) 27/09/2024 FROM 00:01 UNTIL 23:59 HRS.. | 30/09 - 02/10/2024 | 2024-10-02 | 1 JUAN ALFONSO ARENAS DAMIAN Main Chairman 2 ELIZABETH VICTORIA ADELA PAREDES MATTA Main Member 1 3 JAVIER MAMANI PACORI Main Member 2 4 KEVIN ANDERSON RAMIREZ SARAVIA Substitute President 5 LIZ MABEL SIM¿N ROJAS Substitute Member 1 6 BECHER CRISTOBAL CAPCHA CHAVEZ Substitute Member 2 | SUMMONED…
6 | CP-SM-14-2024-MTC-20-1 | ROAD MANAGEMENT AND MAINTENANCE SERVICE BY SERVICE LEVELS OF THE ROAD CORRIDOR: EMP. PE-3S (HUAYLLAPAMPA)-QUINUA - TAMBO- ROSARIO- SAN FRANCISCO - EMP. PE-28C (KIMBIRI) | 187112458.31 | 16/08/2024 UNTIL 30/09/2024 | 16/08/2024 UNTIL 29/08/2024 | 2024-09-19 | Submission of bids (Electronic) 01/10/2024 FROM 00:01 UNTIL 23:59 HRS.. | 02 - 04/10/2024 | 2024-10-04 | 1 PERCY NEYER LOPEZ MEDINA Main Chairman 2 CINDY MARISOL CORTES OLANO Main Member 1 3 JOEL EDILBERTO BULLON CHURAMPI Main Member 2 4 MILUSKHA PAMELA COJAL VIGO Substitute President 5 DANGELO HENRY PACHECO TRUJILLO Substitute Member 1 6 EMERSON JUNIOR SANTON MEZA Substitute Member 2 | SUMMONED...16 SEPTEMBER 2024: Postponed due to validation of the referential value and plurality of bidders.
7 | CP-SM-2-2024-MTC-20-1 | CONTRACTING OF THE CONSULTANCY SERVICE FOR THE SUPERVISION OF THE EXECUTION OF THE WORKS: CONSTRUCTION OF THE JUANA RÍOS BRIDGE AND ACCESSES. | 11141813.7 | 23/07/2024 UNTIL 13/10/2024 | 23/07/2024 UNTIL 09/08/2024 | 2024-09-30 | Submission of bids (Electronic) 14/10/2024 FROM 00:01 UNTIL 23:59 HRS.. | 15 - 17/10/2024 | 2024-10-17 | 1 SVEN HART BAUTISTA CONDORI Main Chairman 2 JOEL EDILBERTO BULLON CHURAMPI Main Member 1 3 HARLEM BRAVO CASTAÑEDA Main Member 2 4 LUIS ADOLFO SUAREZ LEYVA Substitute President 5 EMERSON JUNIOR SANTON MEZA Substitute Member 1 6 JHONNY ALEX ORIZANO PEREZ Substitute Member 2 | SUMMONED…
8 | CP-SM-15-2024-MTC/20-1 | CONTRACTING OF THE CONSULTANCY SERVICE FOR THE SUPERVISION OF THE EXECUTION OF THE WORKS: CONSTRUCTION OF 11 ROAD BRIDGES ON THE NATIONAL ROAD NETWORK ROUTE PE-1NR IN THE TAMBOGRANDE - MORROPÓN - CHULUCANAS PIURA STRETCH. | 30008226 | 11/09/2024 UNTIL 13/10/2024 | 11/09/2024 UNTIL 24/09/2024 | 2024-10-01 | Submission of bids (Electronic) 14/10/2024 FROM 00:01 UNTIL 23:59 HRS.. | 15 -21/10/2024 | 2024-10-21 | 1 JHONNY ALEX ORIZANO PEREZ Main Chairman 6 JUAN JESUS VENTURA ROQUE Main Member 1 3 JUAN ALFONSO ARENAS DAMIAN Main Member 2 2 HARLEM BRAVO CASTAÑEDA Substitute President 5 RODOLFO SAMUEL CHIRI UBILLUS Substitute Member 1 4 JOEL EDILBERTO BULLON CHURAMPI Substitute Member 2 | SUMMONED…
9 | CP-SM-17-2024-MTC/20-1 | PERIODICAL MAINTENANCE OF THE SANTA -CHUQUICARA STRETCH | 72197024.92 | 17/09/2024 UNTIL 20/10/2024 | 17/09/2024 UNTIL 30/09/2024 | 2024-10-09 | Submission of bids (Electronic) 21/10/2024 FROM 00:01 UNTIL 23:59 HRS.. | 22 - 24/10/2024 | 2024-10-24 | 2 GUISELA MARTINEZ ORE Main Chairman 6 MANUEL AUGUSTO ARICA CASTRO Main Member 1 3 CINDY MARISOL CORTES OLANO Main Member 2 1 JUAN CARLOS CASTILLO VASQUEZ Substitute President 4 IRMA MARLEN CERNA DENEGRI Substitute Member 1 5 LUZ DIANA CAMACUARI SUAREZ Substitute Member 2 | SUMMONED…
10 | CP-SM-18-2024-MTC/20-1 | SERVICE OF ROAD MANAGEMENT AND CONSERVATION BY SERVICE LEVELS OF THE ROAD CORRIDOR: PE 20: TRAJECTORY: EMP. PE-1N (I.V. ZAPALLAL) - VENTANILLA - OV. 200 MILLAS - AV. GAMBETTA - PTO. CALLAO, INCLUDING THE OPERATION AND MAINTENANCE OF THE GAMBETTA TUNNEL. | 206442317.38 | 18/09/2024 UNTIL 20/10/2024 | 18/09/2024 UNTIL 01/10/2024 | 2024-10-10 | Submission of bids (Electronic) 21/10/2024 FROM 00:01 UNTIL 23:59 HRS.. | 22 - 28/10/2024 | 2024-10-29 | 1 BRYAN HAL STUARD RIVERA Main Chairman 2 IRMA MARLEN CERNA DENEGRI Main Member 1 3 JACK URBANO PERALTA DELAO Main Member 2 4 MARIA CECILIA PI¿AN INDACOCHEA Substitute President 5 DANGELO HENRY PACHECO TRUJILLO Substitute Member 1 6 JAVIER RODOLFO MATEO UGAZ Substitute Member 2 | SUMMONED…

## PROCESOS CON BASES INTEGRADAS
PRESERVATIONS Provias Nacional - 2024
# | NOMENCLATURE | NAME | AMOUNT | PARTICIPANTS REGISTRATION | INQUIRES AND OBSERVATIONS | BASE INTEGRATION | PRESENTATION | QUALIFICATION | CONFIRMATION | COMMITTEE | COMMENTS
[7 empty] | Submission of Bids (Electronic) 16/09/2024 FROM 00:01 UNTIL 23:59 HRS.. |  |  |  | SUMMONED…...HAS INTEGRATED BASES, FOR THE PRESENTATION OF BIDS ACCORDING TO THE SCHEDULE.

## PROCESOS - ELEVADOS
PRESERVATIONS Provias Nacional - 2024
# | NOMENCLATURE | NAME | AMOUNT | PARTICIPANTS REGISTRATION | INQUIRES AND OBSERVATIONS | BASE INTEGRATION | PRESENTATION | QUALIFICATION | CONFIRMATION | COMMITTEE | COMMENTS
1 | LP-SM-12-2023-MTC/20-1 | CONSTRUCTION OF THE JUANA RIOS BRIDGE AND ACCESS ROADS | 86783171.61 | 26/08/2023 UNTIL 10/01/2024 | 26/08/2023 UNTIL 11/09/2023 | 2023-12-28 | SUBMITTED 05 JANUARY 2024.RUC/Code20556295281 Name or Company Name TABLEROS Y PUENTES S.A. PERU BRANCH | 12 - 17/01/2024 | 2024-01-17 | 1 EDILBERTO SANTIAGO RIVEROS ESQUIVEL Main President 2 Jorge Luis Espinoza Alvaro Main Member 1 3 HARLEM BRAVO CASTAÑEDA Main Member 2 4 FREDDY MANCHA CASO Substitute President 5 LUIS ADOLFO SUAREZ LEYVA Substitute Member 1 6 JHONNY ALEX ORIZANO PEREZ Substitute Member 2 | SUMMONED...BASES INTEGRATED, FOR SUBMISSION OF BIDS AS PER CHRONOGRAM.